## 🌌 Overview
⭐ ORION — Feature Roadmap
Deep Space Habit Tracker — iOS App ¦ Study & Gym ¦ Dark Theme
📊 FEATURE SUMMARY
Total Features |  | Study Features | Gym Features | Integrations | Gamification
🎯 PRIORITY LEGEND
● High |  | ● Medium | ● Low | ● Nice-to-Have
🚀 RELEASE PHASES
v1.0 — MVP | Core streaks, study/gym log, history
v1.1 — Depth | Pomodoro, progressive overload, HealthKit, Widgets
v1.2 — Intelligence | Spaced repetition, body metrics, Weekly Review
v2.0 — Platform | Watch app, Siri, Focus Mode, AI insights
🗂 QUICK NAVIGATION
➜ 📚 Study
➜ 🏋 Gym
➜ 🌌 New Sections
➜ 🔗 Integrations
➜ 🎮 Gamification
Orion — Feature Roadmap ¦ Generated: 21 Apr 2026 ¦ Nishant Bhosale

## 📚 Study
📚 Study Features
Feature | Category | Description | Priority | Phase | Status | Effort | Dev Notes / Implementation Hint
Pomodoro Timer | Focus | 25 min focus / 5 min break cycles with cosmic countdown ring. Each completed pomodoro adds a star to today's constellation. | High | v1.1 | Planned | Medium | Integrate with existing study timer in StudyLogView. Canvas star added per pomodoro.
Focus Score | Session Quality | After each session, rate concentration 1–5 stars. Track average focus score per subject over time to surface best study windows. | High | v1.1 | Planned | Small | Add @Model field focusScore: Int? to StudySession. Show trend in StudyHistoryView.
Distraction Tally | Session Quality | Single-tap +1 distraction counter during a live session. Shows total distractions vs session length as a focus quality ratio. | Medium | v1.2 | Backlog | Small | Tap counter overlaid on timer screen. Store distractionCount: Int in StudySession.
Mood Before / After | Session Quality | Quick emoji picker (😴→🔥) logged with each session. Surfaces patterns like 'you study better after gym'. | Medium | v1.2 | Backlog | Small | moodBefore: Int, moodAfter: Int fields. Correlation shown on Weekly Review screen.
Syllabus Tracker | Progress | Define a course/syllabus with chapters. Each study log marks a chapter complete. Curriculum progress bar shows % done. | High | v1.1 | Planned | Large | New @Model: Syllabus, Chapter. StudySession links to a chapter. New SyllabusView screen.
Spaced Repetition Reminders | Progress | Auto-schedules revision notifications for studied modules (Day 1 → 3 → 7 → 21). Notifies: 'Time to revise AOP Module'. | High | v1.2 | Backlog | Large | Store nextRevisionDate per module. NotificationManager schedules per SM-2 algorithm.
Weekly Study Goal | Progress | Set weekly hour target (e.g. 15 hrs/week). Cosmic orbit ring fills weekly, resets every Monday. | Medium | v1.1 | Planned | Small | @AppStorage weeklyStudyGoalHours. OrbitProgressRing on Home/Study screens.
Subject Heat Map | Analytics | Calendar where each day's colour intensity = hours studied that day. Identify cold spots across subjects. | Medium | v1.2 | Backlog | Medium | Group StudySessions by date+subject. Render as grid in StudyHistoryView.
Session Notes Search | Productivity | Full-text search across all session notes and module names. Find any topic you've ever studied. | Low | v1.2 | Backlog | Medium | SwiftData #Predicate search on moduleName, topicDetail, notes fields.
Study Playlist Link | Productivity | Attach a Spotify/Apple Music playlist URL to a study session. Quick-launch music before starting. | Nice-to-Have | v2.0 | Backlog | Small | Store playlistURL: String? in StudySession. Open via UIApplication.open().
Total: 10 features ¦ Generated: 21 Apr 2026 ¦ Orion — Feature Roadmap

## 🏋 Gym
🏋 Gym Features
Feature | Category | Description | Priority | Phase | Status | Effort | Dev Notes / Implementation Hint
Progressive Overload Tracker | Performance | Compares today's weight/reps vs last time for each exercise. Auto-flags ⬆️ more / ➡️ same / ⬇️ less. Core muscle-building principle. | High | v1.1 | Planned | Large | Query last GymSession with same exercise name. Show delta badge per exercise row.
One-Rep Max (1RM) Calculator | Performance | Enter working weight + reps → auto-calculates estimated 1RM via Epley formula. Tracks 1RM history for Bench, Squat, Deadlift. | High | v1.1 | Planned | Medium | 1RM = weight × (1 + reps/30). Store in separate PRLog @Model. Trend chart in GymHistoryView.
Volume per Muscle Group | Analytics | Weekly total sets per muscle (chest, back, shoulders, legs, arms). Flags imbalances like 'chest 3× but back only 1×'. | High | v1.1 | Planned | Medium | Tag each ExerciseEntry with muscleGroup enum. Aggregate in GymViewModel. Bar chart on Streak screen.
Rest Timer Between Sets | In-Session | Tap-to-start countdown between sets with haptic feedback when rest ends. Set per-exercise rest targets (90s compounds, 60s isolations). | High | v1.1 | Planned | Medium | Overlay timer on GymLogView. restDurationSeconds: Int on ExerciseEntry. .notification(.success) haptic.
Workout Templates | Productivity | Save a Push Day template (Bench 4×8, OHP 3×10...) and load with one tap. Eliminates re-entering exercises every session. | High | v1.1 | Planned | Large | New @Model: WorkoutTemplate. Template picker sheet on GymLogView. Pre-fills exercise list.
Body Weight Log | Body Metrics | Daily/weekly body weight (kg) log with trend line. Track progress toward weight goals over months. | Medium | v1.1 | Planned | Small | New @Model: BodyMetricLog. Quick-add from Home or a dedicated Metrics tab.
Body Measurements Log | Body Metrics | Monthly tracking of chest, waist, arm, hip measurements. Plot trends on star-chart line graph. | Medium | v1.2 | Backlog | Medium | Add fields to BodyMetricLog: chestCm, waistCm, armCm. Render LineChart in MetricsView.
Personal Records (PRs) | Gamification | Auto-detects when you beat a previous best weight or rep count. Celebrates with a gold constellation animation. | High | v1.1 | Planned | Medium | On session save, compare vs historical max. Trigger ShootingStarToast with gold theme + confetti.
Workout Streak by Type | Streak | Separate streak counters for Push/Pull/Leg days. Ensures gym balance — not just total days but PPL balance. | Medium | v1.2 | Backlog | Medium | Track lastPushDate, lastPullDate, lastLegDate in StreakData. Show on StreakView as mini-cards.
Cardio Tracker | Cardio | For cardio sessions: track distance (km), duration, pace (min/km), calories (manual or HealthKit). Trend over weeks. | Medium | v1.2 | Backlog | Large | Add CardioEntry struct alongside ExerciseEntry. Detect workoutType == .cardio to show cardio fields.
Superset / Circuit Logging | Advanced | Group exercises into supersets or circuits. Log them as a block with shared rest time. | Low | v1.2 | Backlog | Large | exerciseGroupType: .single ¦ .superset ¦ .circuit on ExerciseEntry. UI grouping in list.
Total: 11 features ¦ Generated: 21 Apr 2026 ¦ Orion — Feature Roadmap

## 🌌 New Sections
🌌 New Sections Features
Feature | Category | Description | Priority | Phase | Status | Effort | Dev Notes / Implementation Hint
Energy & Recovery Dashboard | Wellness | Tracks sleep hours, energy level (1–10), muscle soreness (body silhouette tap). Correlates energy with study focus and gym performance. | High | v1.2 | Backlog | Large | New screen EnergyView. New @Model: DailyEnergy. Read sleep from HealthKit optionally.
Weekly Review — Star Chart | Analytics | Auto-generated Sunday summary: study hrs vs last week, gym sessions, top module, best workout, one AI insight card. Shareable image. | High | v1.2 | Backlog | Large | WeeklyReviewView auto-opens on Sunday. Use ImageRenderer to export summary as PNG for sharing.
Goals & Missions | Motivation | Longer-horizon goals: 'Complete Spring Boot by May 30', 'Hit 100kg bench by June', '60 study hours this month'. Progress bar + countdown. | High | v1.1 | Planned | Large | New @Model: Mission. MissionsView as a tab or section on Home. Completing unlocks constellation badge.
Journal / Notes Feed | Reflection | Lightweight daily journal tied to habit logs. Auto-populates today's stats, free text area. Searchable personal log of the journey. | Medium | v1.2 | Backlog | Medium | New @Model: JournalEntry. JournalView as bottom sheet or dedicated tab. Full-text search.
Onboarding Flow | UX | First-launch modal: name input + daily reminder time picker + study/gym goal setup. Sets all @AppStorage defaults cleanly. | High | v1.0 | Planned | Medium | OnboardingView shown once via @AppStorage hasCompletedOnboarding flag. 3 steps max.
Settings Screen | UX | User name, avatar, daily reminder time, study goal (min/day), gym goal (sessions/day), weight unit (kg/lbs), notification toggles. | High | v1.0 | Planned | Medium | SettingsView + SettingsViewModel. All values via UserPreferences @AppStorage keys enum.
Streak Freeze — Comet Shield | Streak | Earn one Comet Shield per 30-day streak. Spend it to protect streak if you miss a day. Visual shield badge on StreakView. | Medium | v1.2 | Backlog | Medium | Add cometShields: Int to StreakData. StreakUseCase checks shields before resetting streak.
Total: 7 features ¦ Generated: 21 Apr 2026 ¦ Orion — Feature Roadmap

## 🔗 Integrations
🔗 Integrations Features
Feature | Category | Description | Priority | Phase | Status | Effort | Dev Notes / Implementation Hint
Apple HealthKit | Health | Read: steps, heart rate, active calories, sleep. Write: workout sessions. No manual entry needed for body metrics or cardio. | High | v1.1 | Planned | Large | HealthKit entitlement. HealthKitManager.swift. Request permissions on Energy/Body Metrics screens.
Apple Watch App | Platform | Start/stop study and gym timers from wrist. Glanceable streak + today's progress. Watch complication for lock screen. | High | v2.0 | Backlog | X-Large | New WatchKit Extension target. WCSession for phone-watch sync. WatchConnectivity framework.
Siri Shortcuts | Voice | 'Hey Siri, start study session' or 'Log Push day' — pre-fills the log form. Custom AppIntent per action. | High | v1.2 | Planned | Medium | AppIntents framework. StartStudySessionIntent, LogGymSessionIntent. Siri shortcut donation on first use.
Home Screen Widgets | Platform | 3 sizes: Small (streak + number), Medium (today study + gym status), Large (full weekly summary with orbit rings). | High | v1.1 | Planned | Large | WidgetKit extension target. WidgetProvider reads shared AppGroup SwiftData store.
Lock Screen Widgets | Platform | Streak number + today's completion checkmarks visible on lock screen without opening the app. | Medium | v1.1 | Planned | Medium | WidgetKit accessoryCircular and accessoryRectangular families. iOS 16+ only.
Focus Mode Integration | Automation | When iPhone Focus Mode = 'Study', auto-start study timer in Orion. When Focus ends, prompt to log the session. | Medium | v1.2 | Backlog | Medium | Focus Filters API. FocusFilterIntent. Listen for Focus changes via NSExtensionContext.
Calendar Integration | Smart Input | Read scheduled events — if 'DSA Lecture' is on calendar, pre-suggest the module name in study log form. | Medium | v1.2 | Backlog | Medium | EventKit framework. Read-only calendar access. Fuzzy match event title to module name field.
Share Sheet | Social | Share today's streak, weekly summary card, or a PR achievement as an image to WhatsApp/Instagram. | Low | v1.2 | Backlog | Small | ImageRenderer to PNG. UIActivityViewController. Custom share card matching cosmic aesthetic.
Total: 8 features ¦ Generated: 21 Apr 2026 ¦ Orion — Feature Roadmap

## 🎮 Gamification
🎮 Gamification Features
Feature | Category | Description | Priority | Phase | Status | Effort | Dev Notes / Implementation Hint
XP System | Progression | Every session earns XP (longer = more XP). XP unlocks cosmetic themes (Andromeda theme, Milky Way background variant). | High | v1.2 | Backlog | Large | XP formula: durationMinutes * multiplier (study=1.2, gym=1.0). Store totalXP in UserProfile @Model.
Orion Rank System | Progression | Ranks tied to lifetime hours: Stardust → Nebula → Pulsar → Quasar → Supernova. Shows on Home screen header. | High | v1.2 | Backlog | Medium | Rank thresholds: 10h, 50h, 200h, 500h, 1000h. Computed property on UserProfile. Animated rank-up screen.
Milestone Badges | Achievement | Constellation badges for streaks (7, 30, 100 days), total hours, first PR, first mission complete. Lit vs grayscale+lock states. | High | v1.0 | Planned | Medium | Badge definitions in BadgeRegistry.swift. Evaluated on each session save. 12 badges in v1.0.
Challenge Mode | Motivation | Time-limited challenges: 'Study 10 hours this week', 'Complete full PPL week'. Accept/decline with a swipe. | Medium | v1.2 | Backlog | Large | New @Model: Challenge. ChallengeView. Weekly auto-generated challenges based on user history.
Streak Multiplier | Streak | Streaks above 7 days earn a 1.1× XP multiplier. Above 30 days: 1.25×. Above 100 days: 1.5×. Shown as flame intensity on Home. | Medium | v1.2 | Backlog | Small | Multiplier computed from currentStreak in StreakUseCase. Applied in XP calculation.
Smart Session Suggestions | AI | Based on history, suggests 'You usually study DSA on Tuesday mornings — want to log a session?' Smart nudges. | Low | v2.0 | Backlog | Large | Pattern analysis on StudySession dates. On-device CoreML or simple heuristic in SuggestionEngine.swift.
Fatigue Warning | AI | If trained 4+ consecutive days with no rest, shows soft warning: 'Your body may need recovery — consider a Rest day'. | Low | v2.0 | Backlog | Medium | StreakUseCase checks consecutive gym days. Warning badge on Home gym card. Never blocks logging.
Study Pattern Insights | AI | 'Your focus score drops 40% after 90 minutes — consider shorter sessions'. Derived from focusScore + duration history. | Low | v2.0 | Backlog | Medium | InsightEngine.swift analyses last 30 sessions. Insight card on Home if pattern detected with p > 0.7.
Total: 8 features ¦ Generated: 21 Apr 2026 ¦ Orion — Feature Roadmap

## ✅ Tracker
✅ Orion — Implementation Tracker
Update Status and Sprint as you implement each feature. Use this as your sprint board.
Feature | Category | Priority | Phase | Status | Sprint / Version | Started Date | Done Date | Owner / Notes
Onboarding Flow | UX | High | v1.0 | Planned
Settings Screen | UX | High | v1.0 | Planned
Milestone Badges | Achievement | High | v1.0 | Planned
Pomodoro Timer | Focus | High | v1.1 | Planned
Focus Score | Session Quality | High | v1.1 | Planned
Syllabus Tracker | Progress | High | v1.1 | Planned
Progressive Overload Tracker | Performance | High | v1.1 | Planned
One-Rep Max (1RM) Calculator | Performance | High | v1.1 | Planned
Volume per Muscle Group | Analytics | High | v1.1 | Planned
Rest Timer Between Sets | In-Session | High | v1.1 | Planned
Workout Templates | Productivity | High | v1.1 | Planned
Personal Records (PRs) | Gamification | High | v1.1 | Planned
Goals & Missions | Motivation | High | v1.1 | Planned
Apple HealthKit | Health | High | v1.1 | Planned
Home Screen Widgets | Platform | High | v1.1 | Planned
Weekly Study Goal | Progress | Medium | v1.1 | Planned
Body Weight Log | Body Metrics | Medium | v1.1 | Planned
Lock Screen Widgets | Platform | Medium | v1.1 | Planned
Spaced Repetition Reminders | Progress | High | v1.2 | Backlog
Energy & Recovery Dashboard | Wellness | High | v1.2 | Backlog
Weekly Review — Star Chart | Analytics | High | v1.2 | Backlog
Siri Shortcuts | Voice | High | v1.2 | Planned
XP System | Progression | High | v1.2 | Backlog
Orion Rank System | Progression | High | v1.2 | Backlog
Distraction Tally | Session Quality | Medium | v1.2 | Backlog
Mood Before / After | Session Quality | Medium | v1.2 | Backlog
Subject Heat Map | Analytics | Medium | v1.2 | Backlog
Body Measurements Log | Body Metrics | Medium | v1.2 | Backlog
Workout Streak by Type | Streak | Medium | v1.2 | Backlog
Cardio Tracker | Cardio | Medium | v1.2 | Backlog
Journal / Notes Feed | Reflection | Medium | v1.2 | Backlog
Streak Freeze — Comet Shield | Streak | Medium | v1.2 | Backlog
Focus Mode Integration | Automation | Medium | v1.2 | Backlog
Calendar Integration | Smart Input | Medium | v1.2 | Backlog
Challenge Mode | Motivation | Medium | v1.2 | Backlog
Streak Multiplier | Streak | Medium | v1.2 | Backlog
Session Notes Search | Productivity | Low | v1.2 | Backlog
Superset / Circuit Logging | Advanced | Low | v1.2 | Backlog
Share Sheet | Social | Low | v1.2 | Backlog
Apple Watch App | Platform | High | v2.0 | Backlog
Smart Session Suggestions | AI | Low | v2.0 | Backlog
Fatigue Warning | AI | Low | v2.0 | Backlog
Study Pattern Insights | AI | Low | v2.0 | Backlog
Study Playlist Link | Productivity | Nice-to-Have | v2.0 | Backlog
Total: 44 features ¦ Sorted by Phase → Priority ¦ Generated: 21 Apr 2026